## Development Effort
Development Effort & Cost Estimation (MD & USD)
AI Document Audit & Knowledge Assistant System
Team: 5 (1 PM, 2 Backend, 1 Frontend, 1 QA) · Timeline: 3 months
Task | Man-Days
1.1 Project Setup & Cloud Infrastructure
Architecture & tech stack finalization | 4
Azure resource provisioning (Entra ID, Blob, AI Search, OpenAI, PostgreSQL, Redis, VNet) | 6
CI/CD pipeline (GitHub Actions / Azure DevOps) | 4
Monitoring & logging setup (App Insights, alerts) | 2
Subtotal | 16
1.2 Authentication & Authorization (FR-1)
Azure Entra ID app registration & OAuth2/OIDC configuration | 2
Backend JWT validation & FastAPI auth middleware | 2
RBAC (Vendor / Customer role enforcement) | 2
Login/logout UI (React) | 2
Subtotal | 8
1.3 Frontend Application (React SPA)
Project scaffolding, routing, shared components | 6
Document submission & checklist UI | 8
Audit report viewing & evidence browsing UI | 8
Accept/reject decision workflow UI | 6
Natural language search / Q&A interface | 10
Audit template management UI | 6
Document source addition UI | 4
Expert identification UI | 4
Responsive design & cross-browser polish (Chrome/Edge 130+) | 4
Subtotal | 56
1.4 Backend API (Python / FastAPI)
Project scaffolding, DB models (PostgreSQL), migrations | 6
Document upload & submission API (incl. Blob Storage) | 6
Audit template CRUD API | 4
Audit report & review decision API | 6
Search query API (NL → AI Search → OpenAI) | 8
Expert identification API | 4
Document source connector API (SharePoint, Confluence, file servers, DB) | 8
Interaction logging & feedback API | 4
Subtotal | 46
1.5 Document Processing Pipeline (FR-3, FR-4)
Azure Content Understanding integration for text/structure extraction | 6
ETL pipeline: extract → chunk → embed → index (Celery + Redis) | 10
AI audit generation engine (Azure OpenAI prompt chains + template engine) | 10
Audit report compilation & storage | 4
Queue-depth autoscaling & staged pipelines (NFR-2) | 4
Subtotal | 34
1.6 AI Search & Knowledge Base (FR-7)
Azure AI Search index schema design | 4
Embedding pipeline integration (text-embedding-ada or similar) | 4
NL query interpretation & intent mapping (Azure OpenAI) | 6
Relevance ranking, filtering, hybrid search | 6
Summary generation with source references | 4
Caching layer (Redis for embeddings & frequent queries) | 2
Subtotal | 26
1.7 Expert Identification (FR-8)
HR / Org Directory integration | 4
Keyword extraction from document content | 2
Matching & ranking algorithm | 4
Subtotal | 10
1.8 Learning from Interactions (FR-9)
Query & feedback capture pipeline | 4
Interaction history storage | 2
Relevance model adjustment based on feedback signals | 4
Subtotal | 10
1.9 Non-Functional Requirements
Performance: streaming (SSE), caching, two-tier retrieval (NFR-1) | 6
Scalability: horizontal autoscaling, staged pipelines (NFR-2) | 6
Availability: idempotent tasks, dead-letter queue, health probes, zone redundancy (NFR-3) | 6
Security: managed identities, Key Vault, VNet + private endpoints, TLS (NFR-4) | 8
Subtotal | 26
1.10 Testing
Unit tests (backend: pytest, frontend: Jest / React Testing Library) | 4
Integration tests (API + DB + Azure service mocks) | 3
End-to-end tests (Cypress or Playwright) | 3
Performance & load tests (locust / k6) | 2
User acceptance testing support | 2
Subtotal | 14
1.11 Deployment, Documentation & Training
Infrastructure as Code (Bicep / Terraform) | 6
Deployment runbook & release management | 4
User manual & system documentation | 4
Stakeholder training & handover | 4
Subtotal | 18
1.12 Risk Buffers
Azure service integration delays (quota limits, API changes) | 10
Requirements clarification / rework | 10
Learning curve on AI/ML components | 8
Subtotal | 28
TOTAL DEVELOPMENT EFFORT: 304 MAN-DAYS
TOTAL DEVELOPMENT COST: 304 x 2000 = 608000 USD

## Infrastructure Cost
Infrastructure Cost Estimation (USD)
AI Document Audit & Knowledge Assistant System
Platform: Azure Cloud
Component | Monthly Cost (USD) | 3-Month Estimate (USD)
Development Phase (3 months)
Azure AI Search | 120 | 360
Azure OpenAI (development/testing quota) | 900 | 2700
Azure Database for PostgreSQL | 150 | 450
Azure Blob Storage + Files | 35 | 105
Azure Cache for Redis | 70 | 210
Azure Monitor / App Insights / Log Analytics | 90 | 270
Key Vault, VNet, private networking & DNS | 60 | 180
CI/CD, test runner, and support tooling | 80 | 240
Estimated Total (Development) | 1505 | 4515
Production Phase (steady state)
Component | Monthly Cost (USD)
Azure AI Search (standard tier, indexing + queries) | 350
Azure OpenAI (production inference + embeddings) | 2500
Azure Database for PostgreSQL | 350
Azure Blob Storage + Files | 120
Azure Cache for Redis | 150
Azure Monitor / App Insights / Log Analytics | 200
Key Vault, VNet, private networking & DNS | 150
Alerting, autoscale support, and operational overhead | 100
Estimated Total (Production) | 3920
Note: Production monthly cost (~$3,920) is below the $5,000/month operating cap.